Questions that I need to clarify (when supervisor is back from sick leave):
What values do we compare?
Do we run the new image through the windows programs and compare with the original data set?
If so, what do we compare (what is the method of comparison, is it an average etc?)
In the tps files, what do the values represent, as the x&y pixel descriptions have discrepancies when viewed in paint?

Goal:
Create database where you can compare new specimen to existing dataset, and obtain probability of a specimen to existing species.

Milestones
1) convert tps file to csv 20160922 (25%)
2) make a script that will read and process the csv file 20160929 (condit. on return of super) (25%)
3) Establish variables that can be used for comparisson of new specimen with database 20161006 (25%)
4) Visual representation of the comparison 20161013 (25%)